Hi all, welcome to Project Management – AKA How to avoid a slow but undreamably costly and destructive train wreck.

First up, this talk is largely about problems I’ve seen in IT projects and how to avoid them. I’d make the point that these issues are found universally across IT, they aren’t restricted to one company and I’d be confident in saying anyone experienced in the IT field would agree with me. If we all pretend we’re perfect no one learns from anyone else’s experiences and that’s just pointless. Also, one of SAP’s mottos is “Tell it like it is” so I’m gunna tell it like it is. For your benefit hopefully.

Second up, a quick plug.

***change***

I’m currently looking to start a Mozilla community here in Brisbane. If anyone’s interested in being a part come and talk to me after the presentation.

OK, have you had some super serious talks? Bit bored by day three? Project Management isn’t normally thought of as a funny topic but I’ll make this as entertaining as possible.

So who am I and why are you listening to me?

I’m Kade Morton and you're listening to me because I submitted a really terrible bio with no notes, and for some reason the CompCon organisers decided to let me speak.

This was my bio:

***change***

Kade Morton is a black sheep left by aliens to mature with his human parents to learn the ways of humanity. It is prophesied he will one day lead the alien invasion of Earth and usher in an era of enslavement for the human race. To this end Kade has held many jobs across many industries such as logistics, finance and the public service, scrutinising the behaviours of humans as he goes. Currently his cover story for planning the impending invasion of Earth is that he holds the position of Project Coordinator with SAP Ariba, coordinating the day to day work of a large multinational project run between the world's largest ecommerce networks.

I actually submitted that. Bet you wish you sat this talk out, huh? When digging up my submission I found there was even a spelling mistake in it too, terrible.

Serious though, I work for SAP Ariba, one of the companies under SAP. I went looking for SAP memes and found these.

***change***

We do business process software and for the last seven months I've been working on a project that involves taking all the users of one ecommerce network SAP owns and moving them to another ecommerce network SAP also owns to unify them. We have some of the worlds largest mining companies on the network

***change***

along with every company that sells them things as exciting as dynamite

***change***

to things as boring as pencils,

***change***

and we are shifting them from one network to the other. Sounds simple but the buyers have their own ERP systems (enterprise resource planning systems) designed to work with one network and not the other. So they have work to do their side to integrate to the new network. The sellers might have a similar setup, also meaning work, or they might use the web portal directly, meaning at very least learning a new system. Then you have active documents in one network that need to be copied to the other, like a request for 50 sticks of dynamite, that you can interact with by confirming, rejecting or modifying it, and they are hard to move because the logic the network uses to interpret the code the document is formatted in knows the document came from a set place and contains set things. So if a document came from one network, gets shifted to another and you try to do something with it it might just fail

***change***

because it doesn't recognise where the document came from, where the new document should go, or how to interpret certain pieces of information. Then you have that one of these networks was highly customisable, one is one size fits all and needs to have a heap of features added to account for the customisation. Then you have the fact a mine generating millions of dollars simply cannot shut down because the software failed

***change***

and they can't get their exciting dynamite.

Multiple teams in multiple countries are working on this. It is a complex deployment project, I've lived it for the last seven months and you're listening to me because I can give you my personal perspective on project management and some tips on what to avoid. The students among you might not go on to be project managers but I guarantee if you work in IT you will have to work with a project manager at some point so you will hopefully find this helpful.

***change***

First thing, PM does not stand for Project Management, it stands for Puppet Master.
You cannot be across all the detail. But you do need to be across the high level detail and you need to know what every team is doing at any given time. You need to be able to listen to someone explain something, logically work through it and go “yes that works” or “no you're talking out of your proverbial.” When you spot that things don't make sense you need to challenge people, convince them there's an issue and get them to fix it.

You set the agenda. You pull the strings.

Now, I was once told project management is glorified box checking. That may be true on small non complex projects, but, quite frankly, the person who told me that is a bit of an idiot. Project management is not glorified box checking, it is fire.

***change***

Everything breaks, no one listens to instructions, developers build unusable solutions, and then they bitch and moan about rework, and I just look at them and think “if you built it right first time around we wouldn't be here” which is a problem in technology that deserves its own talk, but the point is project management is fire.

***change***

Tiny problems have the uncanny ability of becoming big problems. You're looking at a bug

***change***

and the bug whispers bro

***change***

this isn't even my final form! Funny story, just after coming up with this slide I ran into an issue during testing and narrowed my eyes, wondering if this little tiny issue was actually a fundamental flaw in the entire underlying software? I raised it as a critical issue with the wider team, the overarching project manager came back and said you've been vindicated, if we had trusted that the software worked like we’d been told, our entire rollout would have been

***change***

derailed.

Now, at its core, project management is like riding a bike, if by riding a bike you mean building and working through a checklist.

***change***

Big technical checklists.

So what should be in your checklist and how do you build it?

***change***

You need to speak to every team involved and find out, at a high level, what goes into what they need to do. You need to map out all the process, end to end, right from the beginning. They key things your looking for are dependencies.

Dependencies are things contingent upon other things. I can't start x until y is done because x uses y. Not mapping out dependences is where you can become undone because you get to x but y was never done so everything has to stop and wait for y. If you have a deadline and a team that cannot work, that's

***change***

 you guessed it, a train wreck. It's a slow moving train wreck because a project will have many parts to it and each takes a set time to complete. You can be in trouble and not even know it. Things can be ticking along fine except your four days away from hitting a five day dependency and even if you realised it right now you're still out by a day, and every day you don't realise it gets worse.

For the technically inclined among you, think of your checklist as a slow running program that has to finish at a set time and every time you hit a bug it takes time to fix.

You can imagine how blown out your deadline can be if you hit multiple dependencies, now imagine the penalties for not delivering on time run into the millions.

***change***

That's how it can be undreamably costly. I've seen a million dollar penalty for failing to meet a contractual deadline, that’s not hyperbole. There are probably bigger ones out there, but I have seen a million dollar penalty. I heard from managers I never even knew existed that day.

***change***

So now you have your map and you know why it’s important. But the fire is in the journey, when the train crashes. So here is some advice to help avoid the train crash.

***change***

As well as mapping out processes you'll be dictating some new processes when you find gaps. Yeah this slide isn’t really that funny. You try finding a relatively PG meme relating to the word gap that doesn’t involve references to thigh gap.

So, gaps in processes. Check that all teams are down with processes. There is nothing like defining a process, then trying to execute the process, and the person doesn't know what they're doing. Or they do it partially. Or they do it shoddily. It's like hitting a dependency that never needed to be there.

***change***

Speak with the development team to validate what was built is what was needed. We've all seen this graphic. It's not just funny, it's true.

On this point, communication is key. Remember how I said the issue with development communicating with other teams deserves its own talk? This is the mini talk.

Poor communication is the biggest problem in IT. Developers are told by functional teams who don’t speak developer what to build, developers don't understand functional and they build something other than what's required. Functional then come back and say the solution can't be used and the two teams go back and forth.

Two examples I've seen. A document the system produces needs to have a unique number on it, so the developers generated the number from the date and time and other factors to make a random number.

It’s unique, right?

However, the number needs to incorporate numbers from other documents in the sequence so when you look at all the documents separately you know what goes together. Yes the developers built something technically correct but it's not usable. You can’t reconcile payments if you can’t tell what order your invoice goes with. If it's not usable your customer will go elsewhere. If customers go elsewhere you have no business. If your company has no business this is you.

***change***

Another example. A survey that a customer can send to their customers to measure performance, it was built to ask for the percentage of what was delivered, have you delivered 100% or 90% or 40% etc of what you agreed to deliver. The survey was being used by a construction company and they were sending the survey to their contractors laying asphalt. The contractors didn't know what percentage of the overall job had been delivered, they just knew how many kilometres of road they'd laid.

I actually overheard the customer yelling at the post sales lady saying the survey was built by someone that doesn’t understand his business. To be fair his language was worse than that and particularly scathing of the developers, but you get the point.

Survey had to be rebuilt to allow for different questions, and the customer clearly wasn't happy. If customers are unhappy they will go elsewhere. Remember what happens to you when that happens?

***change***

You’re still dead. You’ve gotta build things the customer can actually use.

So who's at fault? Both parties, development and functional teams. Functional teams need to learn to talk technical and technical need to talk functional.

Looking at communication in a broader sense, you are dealing with multiple different people, multiple different teams and if you're on a large project multiple different countries.

***change***

I've walked into meetings with particular teams and the overarching project manager says to me, “when you ask a question, lay everything out so there is no ambiguity whatsoever and pin them to an answer.” I didn't really know what she meant, I asked a question about when a particular aspect of the software would be fixed and they said “Next couple of days”. That didn't seem right because I knew other similar issues had taken a lot longer.

Remember how I said you have to assess things and figure out if they sound realistic?

So I said “to be clear, this fix means you need to rework this thing, data cleanse that thing and remap this other thing. Then you need to test it all and work through any problems testing throws up. You are confirming to me all of this will be done in a few days.” and they said “Ahhh… actually now I think about it it will take a lot more time.”

Imagine if I had of taken them at face value and worked to the plan that it was all going to be fixed in a few days?

Now they fully understand the issue and I'm getting a realistic answer the questions become “you can have this done by close of business when exactly? You will have it done by what date specifically?”

What plays into the communication? With this particular team there is a language barrier so I need to check everything I have said has been understood in the way I intended. The onus is on me to check because I don’t know if they misunderstood me. There is also a cultural issue where Australians are seen as very blunt and abrupt, some cultures will just say yes because they think its what you want to hear or just to get you off the phone so they don't have to deal with your bluntness in their face. You need to look at all aspects of the communication.

I assume you are a more technical audience so do not assume everyone understood your very intelligent sounding but technical and jargon laden answer just because you understood it. Just as everyone not technical should educate themselves, everyone technical needs to talk in 'real world' terms. It is a skill that will get you miles.

***change***

test EVERYTHING
On this current project, every tool, every single damn tool I've been given, I've been told doesn't need to be tested, it works fine. We test it and it doesn't work.

Operate under the assumption nothing works until you see it working with your own eyes.
If you test it and it fails, raise it as an issue. If they tell you no its fine, call bull.

Experience I had, I was given reports to run to check statuses of various things on the project. I ran the reports, the results didn't look right, I went into the system and actually compared the system with the report results, could see the report was missing things and flagging things incorrectly. So I went back to the global team and said the reports don't work, here's proof.
They said no no, it works in the other regions.
I said that's not possible, I have incontrovertible proof the report is wrong.
They told me I was being difficult.
I said well give me a report that works and I'll stop being difficult.
They asked why I wasn't performing all these steps that required the report results, I said because you haven't given me a report that works. Some of these things I’m reporting on are legal requirements, and I know for the fact the reports are not working. I’m not going to put the company at risk and I'm not pressing ahead with processes based on incorrect and incomplete data, that's like building a house out of rooting wood.
I asked them when they were going to fix the reports? Nothing
I asked again when are you going to fix it? Still nothing
They were ignoring all my emails. On everything. Not just this issue.
Few weeks later Latin America in a call are like “oh we ran these reports, they aren't working”
I was like O' rly? Tell me more about these reports that don’t work…
Then global apologised to me, confirmed they found the issue and were fixing it.
Stick to your guns, test things, call bull when they don't work.

When I started in IT I thought testing was just testing, but I've learned there are so many different types of testing.
There's user acceptance testing we run with the buyer to make sure they are happy with the solution.
Testing functionality is actually testing testing, we introduced something new, does it work, does it play nice with everything else, did it break anything?
Then there’s Piloting which is going live but closely monitoring to address any bugs. If a pilot is successful the solution is considered to be live.
The overarching PM is always snapping at me, I'm like we're testing and she's like “No Kade, it's called piloting!”
There’s regression testing, testing after a change to make sure previously tested things still work. In a perfect world everything would be regression tested but it depends on your resources.

***change***

Try to avoid reinventing the wheel. Again not a terribly funny slide, this is actually serious.

I've sat in meetings two months down the track where the exact thing gets discussed because no one can remember what the decision was.

Sometimes this is hard. I can have anywhere between two to six, seven, eight meetings a day, I can literally start my day in a meeting and never actually leave the meeting until well after close of business because they run back to back. I can't keep minutes for all of them and even if I did, how am I going to be able to find that thing I vaguely recall we discussed roughly maybe two months ago?

We can't keep a ledger with all the questions and answers because everyone has different ways of working, there are multiple document sharing methods different teams use, no one is on them all, then you need to look at different versions of files.

At a big company getting everyone on the same page is hard. I'm still meeting new people on this project seven months in. I was in Prague at a company event and this presenter was talking about how my project is going and I'm like “I've never seen you or heard of you before in my life...”

Lots of people and tracking hundreds upon hundreds of decisions, very very difficult.

If you can, at the outset, try to define how decisions are going to codified and can be referenced in one single place. It sounds easy and we've tried to do it with one document sharing platform and one big ass document, but seriously it’s still an issue. Maybe this is easier for small teams. I don't really have an answer here, just be mindful of this issue and try to address it as best you can.

***change***

Depending on your resource levels, prepare to be flexible, you may have to wear many hats. Things generally fall to the project manager when they have no where else to go because you have a grasp of the overall process. Do not be afraid to learn new things and view this as a practice at self edification, you're now a better person because you learned new skills. You're also a better employee so see it as career improving. Many hats can be stressful and it can stretch you but this is a good thing.

Don’t be like this cat.

***change***

Take some enjoyment in your work. The more moving parts a machine has, the more likely it is to break. Things will break in project management. You can be working with multiple personalities, egos, teams with their own agendas and you might have to actively fight against people. It can be stressful so enjoy what you can. When I'm given presentations that are to be submitted to buyers I secretly remove all the images of Microsoft office products and slip LibraOffice screenshots into presentations. It's like fight club slipping images into film reel, but open source software.

***change***

You think that's excel your looking at?
Fighting the hegemony of proprietary software one slide at a time.
This is how I see myself.

***change***

this is how my friends tell me they see me. So yeah, enjoy you work.

***change***

In conclusion
PM doesn't stand for Project Manager, it stands for Puppet Master, you set the agenda
Project management is fire. Things break, get used to it
Project mangement at its core is just a checklist
You build a checklist by confirming the processes of all the teams involved and map your path to deployment or whatever it is your project happens to be
You are looking for dependencies
Communicate properly
Test EVERYTHING
Try to keep track of decisions made
Be flexable, wear multiple hats
And again, enjoy yourself when you can

I would like to thank you all for laughing or at least muttering nervously at the correct points, are there any questions?

Abstract

Slow but Undreamably Costly and Destructive train wrecks are bad, how do you avoid them? With Good project management, that's how! While being a PM isn't as glamorous as being a rockstar developer or as chic as being sales people rolling in their bonuses, being able to talk to different teams and knowing what to look for are important skills software companies need. From scoping out the clients need, to deploying a solution, projects are part and parcel of working in the software industry and this talk will cover one person's hard earned experience to put you a cut above the rest to manage real software projects in the real world.

The presentation will cover the theory of what project management is and what it entails in practice. It will look at mapping out the processes of the project and the processes of the different teams involved, the things to look out for like dependences. What dependences are and how not paying attention to them can make your train crash will be covered. The importance of communication among team that speak different languages and being that bridge between different worlds will be looked at. The importance of testing will be emphasised, heavily, along with the different types of testing required. Memes, jokes and general humour may or may not be used to convey these points.